## Slide 1
Ageing Management
and
Long Term Operation Programs
(regulation, activities, planning, organizational aspects)
IAEA SALTO Workshop (28 – 31 May 2013)
C.N. Laguna Verde
Veracruz (México)
J.M. Figueras (CSN-SIN-GEMA, Spain)

## Slide 2: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
INDEX
Ageing Management Review (AMR) for Plant Life Management (PLiM) in Spain
Long Term Operation (LTO) in Spain
3. Planning and Organizational Aspects in Spain
4. Typical aspects to be considered in AMR and AMP for PLiM and LTO

## Slide 3: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
AGEING MANAGEMENT REVIEW (AMR) for PLiM in Spain
CSN requested spanish utilities since mid 90´s, through the Operating Permit conditions, to perform ageing management review plans (AMR) as well as submit a yearly report on AMR activities.
All spanish NPP AMR has been inspected and assessed by CSN routinely, since 1998.
Since 2001 spanish NPP applied USNRC 10CFR54 (Renewal Rule) criteria and methodology for their AMR and AMP.
In 2009 CSN developed national guidance for developing AMR during PLiM (i.e. during 40 years design life-time) and for long term operation (LTO), as well as CSN internal procedures for AMR regulatory assessment and inspection tasks.

## Slide 4
IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México)
Ageing Management and Long Term Operation Programs

## Slide 5: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
Spanish guidance for licensees as well as CSN internal procedures on AMR and LTO has been based on USNRC License Renewal rulemaking:
  10CFR54 (License Renewal), rev. 1995
  RG 1.188 (Standard Format), rev. 1, 2005 -> NEI Guideline 95-10, rev. 6, 2005
  NUREG-1800 (Standard Review Plan), rev. 2, 2010 (methodology for assessment)
  NUREG-1801 (GALL), rev. 2, 2010 (ageing mechanisms and effects; applicable AMP and TLAA)
  Other Rules: 10CFR50.48 (Fire protection), 49 (Environmental qualification), 61 (RPV PTS), 62 (ATWS) and 63 (Station blackout)
  NRC Inspection Manual procedures, 2516 (policy & guidance), 71002 (inspections) and 71003 (LR post approval)
  Other guidance applied:
  IAEA Safety Guides (NS-G-2.12, SALTO Guidelines, etc.)
  WENRA recommendations on ageing management

## Slide 6: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
CSN Safety Instruction IS-22 “Safety requirements for ageing management and LTO of NPP”, July 2009, is mandatory for all NPP.
  AMR is linked to the Periodic Safety Review (every 10 years), as a specific chapter of “PSR dossier”, with special provisions in case design life (40 years) is exceeded.
  IS-22 defines two main NPP life periods: design life (≤ 40 Y) and LTO (> 40 Y).
  IS-22 also defines an “intermediate” phase (before reaching end of design life) for preparation of AMR for LTO life period (PIEGE, in spanish) -> described later.
  IS-22 requests yearly reports on AMR periodic results (“Plan de Gestión de Vida” in spanish) for each NPP life period:
    Life Management Plan (PGV) reports during design life (≤ 40 Y)
    Long Term Life Management Plan (PGV-LP) reports during LTO
    (> 40 Y)

## Slide 7: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
  IS-22 consider that Feasibility Studies for LTO and needed Prerequisites (ISI, QAP, EQ,…) does exists in all Spanish NPP, and mainly defines:
  SSC Scoping (only consider safety criteria for SSC)
  S&C Screening (Active / Passive structures & components) -> ageing of active S&C is controlled through CSN Safety Instruction IS-15, equivalent to 10CFR50.65 (Maintenance Rule) as well as other NPP typical maintenance programs (ASME O&M, electrical and I&C surveillances, MOV and AOV, snubbers,…)
  AMR (materials, environments, ageing mechanisms, ageing effects, AMP, improvement proposals,…)
  SSC reassessment for LTO (> 40 years), through TLAA on metals fatigue, thermal fragilization, RPV irradiation, environmental qualification, civil structures,…
    TLAA must be identified as early as possible, but need not to be performed until 3-5 years before end of design life.

## Slide 8: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
  IS-22 also defines for each life period (design life / LTO) and for “intermediate” phase:
    Reporting criteria (types and content of reports)
    Time schedules (dates for issuance of yearly reports: 1st Sem.; requirements for PIEGE: 3 years / 1 year before)
  IS-22 give guidance on the content of “intermediate” phase for AMR preparation in LTO life period (PIEGE) -> described later.
  Int. & ext. Op. Ex. is considered as a transversal subject.
B. CSN internal procedures for AM and LTO assessment and inspection tasks:
  CSN procedure PT-IV-105 “Regulatory evaluation of SSC ageing management review”, rev. 0, 2009
  CSN procedure PT-IV-223 “Regulatory inspection of SSC ageing management review”, rev. 1, 2009

## Slide 9: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
C. Current rulemaking situation:
  Instruction IS-22 is under revision (after 4 years application) to improve some aspects (clarification of definitions, scoping and screening criteria, interaction with other activities, obsolescence, reporting schedule, applicability of USA, IAEA and FORO documents,…).
  CSN procedure PT-IV-105 “Regulatory evaluation of SSC ageing management review”, rev. 0, 2009, is been converted to a new CSN Safety Guide SG-XX, in order to give detailed guidance to users (utilities, engineering,…) on how to accomplish IS-22 basic requisites.
  CSN procedure PT-IV-223 “Regulatory inspection of SSC ageing management review”, rev. 1, 2009, is been revised, improving some aspects.
  Instruction IS-22 and new Safety Guide SG-XX are been discussed with spanish utilities (UNESA). All 3 documents will be issued by end of 2013.

## Slide 10: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
D. Other sources on AMR and LTO regulation:
  Instruction IS-22 as well as CSN procedures PT-IV-105 “Regulatory evaluation of SSC ageing management review”, and PT-IV-223 “Regulatory inspection of SSC ageing management review”, and other similar documents from Argentina and Brazil, were used as a basis for developing IAEA sponsored Project PREEV “Regulatory Practices on Ageing and Life Extension” (2009-2011)
  Project PREEV has generated 4 basic documents (Technical Docs):
TD 1: Guide for Regulatory Criteria on Ageing Management (AM) and LTO (similar to IAEA Guide 2-12).
TD 2: Guide for Regulatory Assessment of AM and LTO.
TD 3: Guide for Regulatory Inspection of AM and LTO.
TD 4: Guide for AM Issues in the PSR of NPP (similar to IAEA Guide 2-10, but only for LTO period)
  Currently, these 4 Technical Documents are incorporated in FORO web main page. Also, an IAEA Proceedings Document or TECDOC, containing these 4 Guides, is now under final revision and will be issued in November 2013.

## Slide 11: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
2. LONG TERM OPERATION (LTO) in Spain
Before current 10 years Operating License expires, NPP can apply the renewal, for as much as 10 additional years, incorporating information on PLiM in the PSR dossier, as requested by CSN SG-1.10 “Periodic Safety Review of NPP”.
In case design life will be exceeded during these 10 additional years, according to CSN SG-1.10 and IS-22 provisions, an LTO Application must be included in the PSR package, and must content:
  Integrated Ageing Management Review for Long Term Operation (PIEGE in spanish), including:
    Rulemaking used,
    Criteria applicable for AMR (including TLAA) studies,
    SSC scoping and screening -> for long lived and passive structures and components,

## Slide 12: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
  AMR, including:
    Time Limited Aging Analysis (TLAA) for components and structures
    Definition of new or revised ageing management programs (AMP)
  FSAR Supplement (reporting all new or revised AMPs and all TLAA)
  TS Revision (proposing new or modified TS as result of AMPs and/or TLAA)
  Update of Radiological Impact Study (similar to US EIS, environmental impact)
  Update of Waste Management Plan

## Slide 13: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
TYPICAL PIEGE GENERAL RESULTS:
Scoping process:
  Over 70-80 Systems (mech + elec + I&C)
  Over 60-70 Structures and buildings
Screening process:
  Over 60 Systems
  Over 20 Structures
  5 electrical equipment types or commodities (cables, connections, fuse bases, phase buses, and high voltage insulators)
AMR:
  Over 40 AMP (some not included in GALL and specific for NPP: i.e. CRDH inspection, HVAC units surveillance)
TLAA:
  Over 25-30 Studies (over 20-25 generic, from GALL; some not in GALL and specific for NPP: i.e. reactor building crane cycling study)
  Some TLAA are solved through AMP -> i.e. pressure barrier fatigue analysis and electrical equipment environmental qualification

## Slide 14: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
PLANNING AND ORGANIZATIONAL ASPECTS in Spain
Organization:
  Initially defined by utility organization for PLiM phase:
  PGV content (AMR phases) usually developed by specialized engineering company, under control and approval from utility.
  Typical organization -> set of representatives from 10 or more depts. in-NPP and in headquarter offices (technical services, engineering, mech. maint., elec. maint., ISI, chemistry, operation, fire prevention, safety & licensing, conservation & housekeeping,…)
  Define a Coordinator (from utility, usually located in-plant)
  Define a Plant Life Management Committee (from different utility departments + contracted engineering representatives); meeting periodically (2 to 4 yearly meetings)

## Slide 15: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
PLANNING AND ORGANIZATIONAL ASPECTS in Spain
Planning of activities (1):
  PGV (during NPP design life):
    Must be defined by utility as soon as possible (in Spain since 1999-2000, about 20-25 years before LTO period) and can be developed by specialized engineering companies.
    PGV cover all areas of ageing management (S+S, AMR, AMP, improvements to current programs, definition of TLAA).
    Spanish experience show that PGV can be prepared and ready “to-put-in-service” in about 2-2,5 years.
    As much complete and “in-place” is a PGV for design life period, much easier will be to elaborate a PIEGE for justifying LTO.

## Slide 16: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
PLANNING AND ORGANIZATIONAL ASPECTS in Spain
Planning of activities (2):
  PIEGE (“intermediate” phase for LTO application):
    Also defined by utility and usually developed by specialized engineering companies.
    PIEGE cover all areas of ageing management, some of them by revision or updating of PGV tasks (i.e. S+S, AMR, AMP) and some other are new tasks (i.e. special “one-time inspections” AMP, development of all TLAA,…).
    PIEGE, depending on how well defined and applied in a previous PGV, should be prepared and ready to submittal for regulatory review, in 2-3 years (experience of Almaraz or Cofrentes NPP).
    If there is not such plan (PGV), PIEGE preparation time could rise to 4-5 years (experience of Garoña NPP).

## Slide 17: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
  TYPICAL ASPECTS TO BE CONSIDERED IN AMR AND AMP FOR PLiM AND LTO
Mechanical items
RPV irradiation surveillance (P&T curves; specimen tests)
RPV internals inspection
RCS (Class 1) and Class 2 & 3 lines fatigue monitoring
Safety class piping in-service inspection and pumps & valves testing (ASME XI and ASME O&M)
Structural items
Primary and secondary containment inspection / testing
Other structures monitoring (i.e. masonry walls; water control structures)
Buried piping inspection

## Slide 18: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
Electrical items
Typical electrical components requiring AMR: electric cables and connections, fuse bases (not part of active equipments), phase buses and high voltage insulators.
For electrical and I&C equipment, subjected to 10CFR49 requirements, a plant specific EQ Program must exist since NPP start-up for condition monitoring.
For PLiM design life period, EQ Program is considered as an acceptable AMP. For LTO, EQ Program results must be assessed with a TLAA.

## Slide 19: IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs
Electrical items
Although qualified cables (under 10CFR49 scope) are not included in the GALL cable AMP scope, in light of recent regulation (RG 1.211 + RG 1.218) and R&D information (Projects SCAP, NP-T-3.6), CSN consider that qualified cables are to be included in the Spanish NPP AMP scope.
Consequently, during design life period (< 40 Y), CSN recommend to define an specific AMP “Environmental monitoring program” for identifying in-plant actual environmental conditions (temperatures, humidity, radiation,…), and “potential hot spots” on qualified cables and other electrical components.

## Slide 20
MUCHAS GRACIAS !!
(Y AHORA LAS PREGUNTAS…)
THANK YOU !!
(AND NOW QUESTIONS…)
IAEA SALTO Workshop (May 2013) C.N. Laguna Verde Veracruz (México) Ageing Management and Long Term Operation Programs